## Sheet1
PHASTEx Conversion to English Units - Project
No. | Action item | By
|  | Primary | Secondary | Target date
1 | Change units for input and output including report | Kiran | SN/ACT | 2016-06-03
2 | Change data base values for each sheet so the values are in English units | Kiran | SN/ACT | 2016-06-10
3 | Change calculation equations for English units. | ACT/SN | Kiran | 2016-06-30
4 | Check calculations for accuracy | ACT/SN | Kiran | 2016-07-08
5 | Reformat the report format if necessary. This includes changing units, colors, format (pie chart, Sankey diagram etc.). | Kiran/Gina | SN/ACT | 2016-08-05
6 | Pilot testing by 3 to 5 users from different organizations | SN | ACT/Kiran | 2016-08-05
7 | Feedback and revisions as necessary | ACT/SN/Kiran/Gina |  | 2016-08-19
8 | Final packaging
9 | Posting on AMO web site as a test case